## PEDCO
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-IN-DG-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0946 |  |  | Transmital Date: 5/14/2022
Document Title: Instrument & F&G Junction Box Termination Diagram - EXTENSION OF BINAK B/C MANIFOLD |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0946 |  |  | Transmital Date: 5/14/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه مدارک پیش نیاز این مدرک مانند PID نهایی نمی باشد در صورت تغییر این مدرک تیز باید اصلاح گردد |  | BK-SUR-ENG-INS-01-04474 | 2022-05-29 | درخواست کلرفرمای محترم در نظر گرفته می شود.
2 | ارتباط بین LT موجود بر روی SUMP در این مدرک دیده نشده است |  | BK-SUR-ENG-INS-01-04474 | 2022-05-29 | درخواست کلرفرمای محترم اعمال گردید
3 | لیست مدارک مرجع با شماره رویژن د راین مدرک کامل و اصلاح گردد برای مثال مدرک PID نیز در این مدرک آورده شود |  | BK-SUR-ENG-INS-01-04474 | 2022-05-29 | درخواست کلرفرمای محترم اعمال گردید
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 23 Feb 2022 |  |  |  |  | Date: