## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1087 |  |  | Transmital Date: 19.Jun.2022
Document Title: P&ID - Slug Catcher System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1087 |  |  | Transmital Date: 19.Jun.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0004_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نتايج حاصل از جلسه هاي HAZOP, HAZID, SIL در اين دياگرام اعمال گردد. |  | BK-SSR-ENG-PCS-01-05040 | 09.Jul.2022 | اعمال گردید.
2 | حجم ذخير در لخته گير كمتر از ميزان محاسبه شده لخته توسط آن پيمانكار مي باشد. |  | BK-SSR-ENG-PCS-01-05040 | 09.Jul.2022 | محاسبات مربوطه در مدرک DRUM SIZING ارائه شده است.
3 | با توجه به موارد فوق سايز شير هاي ايمني و خطوط وابسته نياز به بازنگري دارد. |  | BK-SSR-ENG-PCS-01-05040 | 09.Jul.2022 | صحیح می‌باشد.
4 | سايز خط بالادست شير ايمني نياز به بازنگري كلي دارد. |  | BK-SSR-ENG-PCS-01-05040 | 09.Jul.2022 | صحیح می‌باشد.
5 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SSR-ENG-PCS-01-05040 | 09.Jul.2022 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021