## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0653 |  |  | Transmital Date:2/28/2022
Document Title:P&ID - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0653 |  |  | Transmital Date:2/28/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-PI-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در ويرايش جديد مطابق نظر ذينفع اصلي، كلاس خط بالادست از 3000 به 600 تغيير نموده كه مي بايست تبعات فني آن از طرف آن پيمانكار براي ذينفع اصلي شفاف سازي شود. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | اعمال گردید.
2 | كلاس خطوط با آخرين ويرايش PMS مطابقت ندارد و امكان بررسي آن وجود ندارد. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | بر اساس آخرین تغییراتمدرک PMS بازنگری گردید.
3 | سايز شير ESDV 6 اينچ در نظر گرفته شده ، عليرغم آنكه سايز خط 4 اينچ مي باشد. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | اصلاح گردید.
4 | لاجيك كنترلي، مي بايست به تاييد ذينفع اصلي برسد. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | مورد تایید است.
5 | درنظر گرفتن هدر جديد در كلاس 300 باوجود كلاس 600 هدر قديمي، مي بايست به تاييد ذينفع اصلي برسد. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | مورد تایید است.
6 | كامنت پيشين: پاسخ پيمانكار قانع كننده نبوده و نحوه اتصال خط 150پوند 171G به خط با كلاس بالاتر بدون درنظر گرفتن محافظت فشاري تصحيح گردد. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | بر اساس جلسات مطالعات HAZOP کلاس خط 300 در نظر گرفته شده است.
7 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-00-03656 | 2022-03-16 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021