## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-CN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0628 |  |  | Transmital Date: 2/23/2022
Document Title:Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak BC Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0628 |  |  | Transmital Date: 2/23/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اگرچه محاسبات مربوط به NPSH Available پمپ های حوضچه نفت از سوی این امور مورد تایید است در خصوص تغییر و انتخاب نوع پمپ مناسب می بایست بر اساس رویه تغییرات،هر گونه تغییر مدیریت شود و بر اساس رویه تغییرات اقدام شود.بدیهی است در مدت انجام این موضوع مطابق زمانبندی تعریف شده در ارتباط با تغییرات،بایستی فعالیت مهندسی مبنا همچنان ادامه داشته باشد. |  | 1400-2294-445285 | 1400/12/21 | محاسبات بر اساس پمپ Vertical ارایه می گردد. در صورت عدم تایید آن کارفرما محترم در خصوص تغییر تایپ پمپ مدارک مربوطه بازنگری خواهد گردید.
2 | محاسبات Line Sizing ارایه نشده. |  | 1400-2294-445285 | 1400/12/21 | ارسال می گردد.
3 | سناریوهای طراحی شیرهای ایمنی ارایه نشده است. |  | 1400-2294-445285 | 1400/12/21 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: