## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-CV-DC-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-0589 |  |  | Transmital Date:2/13/2022
Document Title:Civil Design Criteria |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-CV-TR-0589 |  |  | Transmital Date:2/13/2022
[5 empty] | CRS No:PEDCO-CRS - D01-BK-GNRAL-PEDCO-000-CV-DC-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد مطروحه درفایل پیوست |  | BK-SUR-ENG-CIV-00-0320 | 2022-02-23 | در فایل پیوست پاسخ داده شده
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: