## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-EL-LI-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0692 |  |  | Transmital Date: 07-Mar-2022
Document Title: Electrical Load List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-EL-TR-0692 |  |  | Transmital Date: 07-Mar-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-EL-LI-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | PEDCO Elec: Regarding to electrical equipment calculation such as AC&DC UPS calculation has not been submitted, so at this stage only structural comments has been mentioned and this document shall be submitted as IFA after submitting prerequisite documents (base on comment 2). |  | BK-SUR-ENG-ELE-00-03603 | 2022-03-15 | توانهای مورد نیاز سیستم AC UPS و باتری شارژر بر اساس آخرین ویرایش بارهای ابزاردقیق ارسال شده در ترنسمیتال 852 در نظر گرفته شده است. در صورت تغییر در لیست بار ابزاردقیق این مدرک به روزرسانی خواهد شد.
2 | PEDCO Elec: This document shall be revised after finalizing or minor comments of following items : -AC/DC UPS calculation. -Vendor data for pumps |  | BK-SUR-ENG-ELE-00-03603 | 2022-03-15 | بعد از دریافت میزان دقیق بارها از سازندگان مربوطه، این مدرک به روزرسانی خواهد شد.
2 | PEDCO Process: load duty for oil sump pump P-207 shall be changed to "Intermittent". |  | BK-SUR-ENG-ELE-00-03603 | 2022-03-15 | به صورت Intermittent در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 15-Mar-22 |  |  |  |  | Date: