## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-01165 |  |  | Transmital Date: 7/17/2022
Document Title: BINAK Oil Field Project Overall Well Location/Facilities Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1165 |  |  | Transmital Date:7/17/2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-CV-PY-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد در شيت تكميلي و يا بصورت پنجره مجزا مي تواند نمايش داده شود |  | BK-SUR-ENG-CIV-01-05221 | 2022-07-24 | با توجه به اینکه این نقشه مربوط به Well Location است لذا محدوده مربوطه نشان داده شده است. ضمن اینکه هدف از ارائه این نقشه داشتن دید کلی در یک نگاه است و تعدد شیت ها کارایی این نقشه را کاهش می دهد. نقشه 1:25000 نیز اضافه شد.
2 | ارائه چنین مدرکی مناسب و عرف نیست و لازم نیست حتما در یک شیت باشد گاها مدرک اینچنینی در چند شیت ارائه میشود اما نه با عکس هوایی. اين جزييات تنها به عنوان شماتيك در كنار نقشه هاي اصلي مي تواند پذيرفته شود |  | BK-SUR-ENG-CIV-01-05221 | 2022-07-24 | اعمال شد. نقشه های 1:25000 در جهت تکمیل نقشه در کنار عکس ماهواره ای قرار داده شد.
3 | جاده دسترسي به GCS با همان شماتيك جاده دسترسي به چاه معرفي شده كه اصلاح شود |  | BK-SUR-ENG-CIV-01-05221 | 2022-07-24 | اصلاح شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date:

## Sheet2
BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001