## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-SP-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0997 |  |  | Transmital Date: 24/MAY/2022
Document Title: Pipeline Material Specification |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-PI-TR-0997 |  |  | Transmital Date: 24/MAY/2022
[5 empty] | CRS No: CRS-BK-SSGRL-PEDCO-110-PL-SP-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | استاندارد BS5351 منقضی شده است و میبایست با استاندارد مناسب جایگزین گردد. |  | 01/2294/135308 | 1401/04/19 | - اعمال گردید
2 | استاندارد API 6A از استاندارد ساخت اتصالات حذف گردد. |  | 01/2294/135308 | 1401/04/19 | - اعمال گردید
3 | آیتم های موجود در صورتجلسه |  |  | 1401/05/12 | تمامی آیتم ها بررسی ودر مدرک اعمال گردید و با توجه به اعمال این موارد ، مدرک با وضعیت AFD ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 07/06/2022 |  |  |  |  | Date: 07/06/2022