## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-CN-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0291 |  |  | Transmital Date: 04/DEC/2021
Document Title: Pipeline Wall Thickness Calculation |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PL-TR-0921 |  |  | Transmital Date: 04/DEC/2021
[5 empty] | CRS No: CRS-BK-SSGRL-PEDCO-110-PL-CN-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PPL-00-02462 | 2021-12-27 | - با توجه به اینکه مباحث مربوطه به کامنهای مطرح شده، به درخواست کارفرما به مدرک BK-SSGRL-PEDCO-110-PI-CN-0001 منتقل شده است، لذا اعمال کامنتها بر روی این مدرک میسر نبوده و در مدرک مذکور بررسی خواهد شد
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 27/12/2021 |  |  |  |  | Date: 27/12/2021