## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-QC-PR-0029_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0629 |  |  | Transmital Date: 23/Feb/2022
Document Title: PIPELINE PWPS (Preliminary Welding Procedure Specification) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-QC-TR-0629 |  |  | Transmital Date: 23/Feb/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-QC-PR-0029_D00 |  |  | CRS Status:
| Comments (NISOC) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | استاندارد IPS-C-PI-270 در فرمت ارائه شده برای WPS نوشته شود و روشهای جوشکاری ارائه شده مطابق آن اصلاح گردد. |  | 01/2294/1320 | 1401/01/06 | به نحو مقتضی اعمال گردید
2 | عدد مربوط به ضخامت اصلاح گردد. |  | 01/2294/1320 | 1401/01/06 | به نحو مقتضی اعمال گردید
3 | زاویه پخ زنی (a) در شماتیک ارائه شده مطابق تصویر شماره 2استاندارد ASME B-16.25 اصلاح گردد. |  | 01/2294/1320 | 1401/01/06 | به نحو مقتضی اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: P.Imani | Signature | M.Fakharian
Date: