## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0007_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0309 |  |  | Transmital Date: 3/12/2022
Document Title:Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0009-IN-TR-0309 |  |  | Transmital Date: 3/12/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| جهت مدارک فوق با توجه به مدرک accuracy. SPEC for Instrument حداقل 0.1 f.S درصد باشد. |  | 00/2294/1301 | 1401/01/06 | در این مدرک دقت 0.1 می باشد و نیاز به تصحیح ندارد.
1 | با توجه به مفاد ماده 13 شرایط عمومی پیمان و نظر به وظایف و مسئولیتهای کامل مالی و قرارداد پیمانکار EPC/EPD ، پس از انجام تصحیح فوق جهت مدارک اشاره شده نظر دیگری مطرح نمی باشد و پیشبرد گام بعدی مهندسی مدرک و انتشار AFC بلامانع می باشد. |  | 00/2294/1301 | 1401/01/06 | ملاحظه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 20 Dec 2021 |  |  |  |  | Date: