## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-ME-DT-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0799 |  |  | Transmital Date: 16/Apr/2022
Document Title: Mechanical Data Sheets For Oil Sump Pump (P-1701) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0101-ME-TR-0799 |  |  | Transmital Date: 16/Apr/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص دبی و چگالی سیال توضیحات مرتبط ارایه گردد. |  | 01/2294/45436 | 1401/02/10 | دانسیته 850 ~ 970 در نظر گرفته شده است و در محاسبات هیدرولیک 970 KG/M3 دانسیته
2 | با توجه به حجم حوضچه دبی پمپ زیاد در نظر گرفته شده است. |  | 01/2294/45436 | 1401/02/10 | مطابق اسناد مهندسی پایه میباشد.
3 | با توجه به ماهیت سیال، چگالی بصورت بازه بیان گردد. (اشاره به یادداشت 28) |  | 01/2294/45436 | 1401/02/10 | نظر کارفرمای محترم اعمال می گردد.
4 | علت تغییر نوع پمپ نسبت به اسناد پیمان توضیح داده شود. با توجه به بازه تغییرات چگالی و گرانروی به نظر می رسد نوع پمپ صحیح در نظر گرفته نشده است. |  | 01/2294/45436 | 1401/02/10 | پمپ مذکور وظیفه تخلیه مایعات و آلودگی های جمع شده به علت تعمیر و تخلیه تجهیزات را دارد. مطابق با مدارک پایه و اسناد مناقصه ، این پمپ از نوع افقی بود ولی برای رفع مشکل NPSHاحتمالی در صورت گرفتگی foot valve ، این پیمانکار پیشنهاد تغییر نوع آن به VS4 را داده تا احتمال وقوع کاویتاسیون بواسطه نبود NPSH مورد نیاز برای پمپ های افقی کاهش یابد.
5 | به شماره P&ID مربوطه در مدرک ارجاع گردد. |  | 01/2294/45436 | 1401/02/10 | نظر کارفرمای محترم اعمال می گردد.
6 | به دلیل نوع و آلودگی سیال، مقصد خروجی پمپ نمی بایست چند راهه (Manifold) ورودی باشد. پیشنهاد این امور تغییر مقصد سیال است. |  | 01/2294/45436 | 1401/02/10 | این مورد در جلسات hazop بررسی گردید و مقرر شد مقصد همان منیفولد بینک باشد.
7 | با توجه به تغییر مقصد سیال، میزان فشار خروجی پمپ مذکور بازبینی گردد. |  | 01/2294/45436 | 1401/02/10 | بر اساس مقصد منیفولد صحیح میباشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 08/28/2022