## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0713 |  |  | Transmital Date:3/9/2022
Document Title: P&ID - Gas Pipeline (to Siahmakan G.I. Station) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0713 |  |  | Transmital Date:3/9/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دریافت کننده توپک بصورت Concentric نمایش داده شود. |  | 1401-2294-43235 | 1401/02/09 | اعمال گردید.
2 | علت افزایش فشار طراحی تجهیزات خط لوله گاز نسبت به ویرایش قبل توضیح داده شود. |  | 1401-2294-43235 | 1401/02/09 | افزایش فشار مقصد در سیاهمکان موجب افزایش فشار خروجی استگاه تقویت فشار گاز بینک ودر نتیجه فشار طراحی خط لوله شده است.
3 | برای هر کدام از Pig Launcher/receiver دو عدد گیج فشاری ، یکی رنج پایین و دیگری رنج بالا در نظر گرفته شود. |  | 1401-2294-43235 | 1401/02/09 | تعداد گیج های فشار بر اساس استاندارد IPS STANDARD DRAWING NO.: S4L-6516 و مدارک پایه در نظر گرفته شده است . در صورتیکه آن کارفرمای محترم اضافه نمودن گیج فشاری در تجهیزات Pig Launcher/receiver الزام آور میداند خواهشمند است مراتب را امر به ابلاغ فرمایند.
4 | در نقشه 0001 ، سایز PSV-3201 با خطوط لوله مطابقت داده شود . |  | 1401-2294-43235 | 1401/02/09 | سایز شیر مربوطه بر اساس محاسبت ارائه شده در مدرک سایزینگ شیر ایمنی در مدرک گزارش گردیده است.
5 | در نقشه 0002 ، سایز LBV ها مشخص گردد. |  | 1401-2294-43235 | 1401/02/09 | اعمال گردید.
6 | در نقشه 0003، در خصوص PSV-3202 سایز لوله در ورودی شیر ایمنی نمی بایست تغییر کند و استفاده از REDUCER صحیح نیست . |  | 1401-2294-43235 | 1401/02/09 | سایز خط ورودی 2 میباشد.
7 | در نقشه 0003 ، NOTE 4 صحیح نمی باشد ، مطابق اسناد پیمان بایستی سیستم کنترل ESD جدید طراحی و اجرا گردد. |  | 1401-2294-43235 | 1401/02/09 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021