## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0029_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0964 |  |  | Transmital Date: 17/May/2022
Document Title: Mechanical Data Sheets For Fire Water Main Pump-Elect.Motor Driven |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-0964 |  |  | Transmital Date: 17/May/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اظهار نظر در خصوص فشار و دبی پمپ منوط به نهایی شدن مدارک هیدرولیک و میزان مصرف آب آتش نشانی خواهد بود. لذا ضمن یادآوری رعایت اولویت بندی ارسال مدارک ضروریست این مدرک با اطلاعات تایید شده مجددا ارسال گردد. |  | 01/2294/102542 | 1401/03/24 | به اطلاع کارفرمای محترم می رساند مدارک اصلاح شده هیدرولیک و محاسبات میزان مصرف آب آتش نشانی پیش از این ارسال گردیده است. لذا خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 08/28/2022