## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-CN-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0766 |  |  | Transmital Date: 30/MAR/2022
Document Title: Piping Wall Thickness Calculation |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0766 |  |  | Transmital Date:30/MAR/2022
[5 empty] | CRS No: CRS-BK-SSGRL-PEDCO-110-PI-CN-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | براي كلاسهاي LN15 و MN15 براي لوله هاي داخل فنس بايستي F برابر 0.6 در نظر گرفته شود. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | - کلاسهای مذکور به ترتیب به LN17 و MN17 تغییر یافته و ضریب طراحی 0.6 منظور گردید.
2 | در بخش 5.2.2 با توجه به محاسبات در كلاسهاي AN15 و LN15 و MN15 بر اساس كد ASME B31.4 بايستي فرمول محاسبات براي اين كد طراحي اضافه گردد. همچنين، با توجه به كامنت كارفرما در صورت نياز بهتر است مطابق IPS-E-PI-140 به كد طراحي ASME B31.8 نيز اشاره گردد. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | - اعمال گردید.
3 | در كلاس AN15 براي سايز 2 اينچ و بالاتر نيز متريال API 5L GR.B ذكر شده و محاسبات بر آن اساس اصلاح گردد. ضخامت لوله 4" همانند PMS برابر 6mm يا Sch.40 ذكر گردد. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | - اعمال گردید.
4 | در جدول محاسبات ضخامت، سرويس ها بر اساس اصلاحات در مدرك PMS اعمال گردد. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | - اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 13/04/2022 |  |  |  |  | Date: 13/04/2022