## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-SP-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0766 |  |  | Transmital Date: 30/MAR/2022
Document Title: Piping Material Specification |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0766 |  |  | Transmital Date:30/MAR/2022
[5 empty] | CRS No: CRS-BK-SSGRL-PEDCO-110-PI-SP-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در كلاس AN15 سرويس بايستي Crud Oil(Burn Pit) معرفي گردد. در جداول بخش 7.2 و 8 اصلاح گردد. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | اعمال گردید.
2 | در كلاس AN04 خط آتش نشاني بصورت Fire Water (AG) ذكر گردد. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | اعمال گردید.
3 | در كلاس AN05 با توجه به ذكر سرويس Fuel Gas در مدرك مطالعات خوردگي سرويس مذكور اضافه گردد. |  | BK-SUR-ENG-PIP-01-03917 | 2022-04-16 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 13/04/2022 |  |  |  |  | Date: 13/04/2022