## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DC-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0993 |  |  | Transmital Date: 23 May 2023
Document Title: Fire & Gas Detection Design Criteria |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0993 |  |  | Transmital Date: 23 May 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DC-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توضیحات ارائه شده در خصوص نقطه نظرات این امور کافی نمی باشد، بنابراین لازم است موارد ابهامی در جلسه ای (هفته پیش رو) با حضور نمایندگان کارفرما و پیمانکار در اهواز، شفاف و اتفاق نظر صورت گیرد (هماهنگی قبلی برای زمان و مکان جلسه و نیز حضور نمایندگان کارفرما انجام گردد.) |  | 00/2294/167265 | 1401/05/13 | مدرک مطابق آخرین صورت جلسه (به تاریخ 1401/05/26)با حضور کارفرمای محترم اصلاح و بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: s.akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 28 Jan 2022 |  |  |  |  | Date: