## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-IN-MR-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0471 |  |  | Transmital Date: 16 Jan 2022
Document Title: PMR For Instrument Bulk Items - W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-IN-TR-0471 |  |  | Transmital Date: 16 Jan 2022
[5 empty] | CRS No: NISCO-CRS-BK-W028-PEDCO-110-IN-MR-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
INSTRUMENT DEPARTMENT COMMENTS
1 | صفحه 6، کلمه client جایگزین purchaser شود. |  | 1400-2294-390714 | 1400/11/11 | اعمال گردید.
2 | صفحه 7 قسمت 6، کلمه client جایگزین purchaser شود. |  | 1400-2294-390714 | 1400/11/11 | اعمال گردید.
3 | عبارت if any از مدرک حذف گردد. |  | 1400-2294-390714 | 1400/11/11 | اعمال گردید.
4 | صفحه 9 قسمت 11، کلمه client جایگزین purchaser شود. |  | 1400-2294-390714 | 1400/11/11 | اعمال گردید.
5 | صفحه 11 قسمت 11، عبارت other fee حذف گردد. |  | 1400-2294-390714 | 1400/11/11 | اعمال گردید.
6 | ویرایش نهایی مدارک جهت پیوست ها در نظر گرفته شود. |  | 1400-2294-390714 | 1400/11/11 | ملاحظه و بررسی می شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 26 Jan 2022 |  |  |  |  | Date: