## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028S-PEDCO-110-PI-MT-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0824 |  |  | Transmital Date:16/Apr/2022
Document Title: MTO FOR FITTINGS – W028S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-PI-TR-0824 |  |  | Transmital Date: 16/Apr/2022
[5 empty] | CRS No: CRS-BK-W028S-PEDCO-110-PI-MT-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر به اينكه هنوز P&ID وPMS و Wall Thickness و Piping Corrosion Study &Material Selection Report و PDMS پروژه تائيد نشده است لذا نظر نهايي پس از تائيد مدارك ذكر شده ارسال مي گردد. |  | BK-SUR-ENG-PIP-01-04061 | 2022-04-06 | مدارک مرتبط تایید شده براساس صورتجلسه اخیر مورخ 1401/05/26 ، ارسال گردید.این مدارک نیز براساس خروجی نتایج صورتجلسه مذکور مورد بازبینی قرار گرفته است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 25/04/2022 |  |  |  |  | Date: 25/04/2022