## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-MR-0006_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0822 |  |  | Transmital Date: 16/Apr/2022
Document Title: PMR FOR BOLT/NUTS– W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-PI-TR-0822 |  |  | Transmital Date: 16/Apr/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0006_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در جدول Attachment 1(List of Reference/Applicable Documents): 1- دستورالعمل Packing, Marking, Transportation Procedure اضافه شود. 2- دستورالعمل Specification for Transportation,Handling,Marking,Storage of Pipes and Other Materials |  | BK-SUR-ENG-PIP-01-04077 | 30.04.2022 | اعمال گردید
2 | برخي از مدارك Attachment 2 براي BOLT/NUTS كاريردي نيست. جدول براي اين نوع كالا اصلاح گردد. |  | BK-SUR-ENG-PIP-01-04077 | 30.04.2022 | لیست مدارک به صورت کلی می باشد ولی با توجه به اضافه نمودن نوت زیر و در VPIS دریافتی تکمیل خواهد گردید.
3 | عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-01-04077 | 30.04.2022 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
Date:30/04/2022