## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-SU-DW-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0802 |  |  | Transmital Date: 11-Apr-2022
Document Title: Over Head Line Plan and Profile - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0101-SU-TR-0802 |  |  | Transmital Date: 11-Apr-2022
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-SU-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | به جهت تسریع در انجام کار، نقشه با در نظر گرفتن حریم، توسط اداره مهندسی نقشه برداری مناطق نفت خیز جنوب اصلاح و با شماره 80370 A در فرمت PDF و DWG در ضمیمه نامه 137402 جهت ادامه مراحل طراحی به حضورتان ارال می گردد. |  | 1401-2294-144181 | 1401-04-27 | با توجه به شرح کار و مطابق با مسیر پیشنهادی، طول مسیر خط هوایی افزایش یافته است که در نتیجه این تغییر، مدرک مورد ویرایش قرار گرفته است. لازم به ذکر است تأثیرات مالی و زمانی این تغییر متعاقبا اعلام خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 24-Apr-2022 |  |  |  |  | Date: