## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-ME-DT-0001-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1276 |  |  | Transmital Date: 15/August/2022
Document Title: Data Sheets For Pig Traps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-ME-TR-1276 |  |  | Transmital Date: 15/August/2022
[5 empty] | CRS No:NISOC-CRS-BK-PPL-PEDCO-320-ME-DT-0001-D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | یادداشت شماره 15 براساس مطالعات HAZOP اصلاح گردد. |  | 01/2294/205540 | 06.09.1401 | طبق مطالعات HAZOP، نیازی به تغییر این بند نمیباشد.
2 | شماتیک ارایه شده در صفحات 5و9 مدرک وضوح نداشته و می بایست اصلاح گردد. لازم به ذکر است انطباق این شماتیک با نقشه هاس استانداردی ضروری است. |  | 01/2294/205540 | 06.09.1401 | اعمال گردید.
3 | میزان خوردگی مجاز در مدرک با نتایج مطالعات خوردگی ارسال شده مغایرت دارد. |  | 01/2294/205540 | 06.09.1401 | میزان خوردگی مجاز منطبق بر مطالعات خوردگی تایید شده (و مدارک پایه قراردادی) میباشد
4 | با توجه به عدم ارایه محاسبات، ضخامت مندرج در صفحه 8 مدرک حذف گردد. |  | 01/2294/205540 | 06.09.1401 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Ghadyani | Signature | M.Fakharian |  |  | Clarified By: | Signature
| Date: 9/03/2022 |  |  |  |  | Date: