## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1072 |  |  | Transmital Date:14-JUN-2022
Document Title: Civil Layout For Pig Receiver Area (In Siahmakan G.I. Station) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1072 |  |  | Transmital Date:14-JUN-2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-CV-PY-0001-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| َA- بخش مهندسی مکانیک |  | 01/2294/113888 | 1401/04/02 | صورتجلسه جانمایی مورخ 1401/06/08 به پیوست ارسال می کند. نقشه بر اساس این صورتجلسه اصلاح شد. (فایل ضمیمه)
1 | مختصات جانمایی شده در این نقشه برای تجهیزات توپک گیر، به تایید این امور و ادارات ذیربط نرسیده است. (ارائه صورتجلسه جانمایی الزامی است).
| B- بخش مهندسی سیویل، سازه و معماری |  | 01/2294/113888 | 1401/04/02 | صورتجلسه جانمایی مورخ 1401/06/08 به پیوست ارسال می کند. نقشه بر اساس این صورتجلسه اصلاح شد. (فایل ضمیمه)
1 | ابعاد سطح و بتن برای این تجهیز (53000 * 1000) به تایید این امور نرسیده است. اقدامات عاجل صورت پذیرد.
2 | موضوع نقشه Layout است. ارائه ی- Pig Receiver Platform Plan (Detail A)- یا با جزئیات کامل دیده شود یا حذف گردد. |  | 01/2294/113888 | 1401/04/02 | اصلاح شد. بزرگنمایی جهت ارائه مختصات چهار گوشه و ابعاد مورد نظر ارائه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: