## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-RT-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1120 |  |  | Transmital Date: 27-JUN-2022
Document Title: Site Visit Report (Civil Work) - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1120 |  |  | Transmital Date: 27-JUN-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK14-PEDCO-110-CV-RT-0001-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | كامنت بخش برق: تعداد دكل هاي انتقال برق در گزارش 7 عدد قيد شده است اما اين تعداد در مدرك Plan and profile خط انتقال برابر شش عدد است لازم است تناقض بين گزارش و مدرك مرجع برطرف گردد |  | BK-SUR-ENG-CIV-01-05019 | 2022-07-06 | اصلاح شد. برای جزئیات به مدرک مربوطه رفرنس داده شد.
2 | شرح كار قراردادي به عنوان حداقل هاي مورد نياز ذينفع اصلي ملاك كار خواهد بود |  | BK-SUR-ENG-CIV-01-05019 | 2022-07-06 | گزارش بر اساس شرح کار اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: