## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-703 |  |  | Transmital Date: 5/9/2022
Document Title: Chemical Consumption List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0703 |  |  | Transmital Date: 5/9/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ميزات تزريق ماده بازدارنده خوردگي پس از اظهار نظر ذينفع اصلي و نيز ارائه اطلاعات از سازنده نهايي سازي مي گردد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | مورد تایید است.
2 | در جدول شماره 1 فشار عملياتي خط نيازمند تزريق درج گردد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اعمال می گردد.
3 | در صفحه 9در خط چهارم محاسبات عدد 0.798 از كجا آورده شده؟ |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اصلاح گردید.
4 | در صفحه 9در بند چهارم محاسبات عدد 12.81نادرست است و بجاي آن عدد 12.34 قيدگردد |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اصلاح گردید.
5 | منطبق نمودن داده هاي جدول 2 صفحه 8 و ساير مصرف كننده ها با مدارك PFD,P&ID ,UFD مي بايست صورت پذيرد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اعمال می گردید.
6 | اظهار نظر درخصوص ميزان تزريق متانول پس از ارائه مستندات و شبيه سازي هاي صورت گرفته امكان پذير خواهد بود. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | فایل محاسباتی به پیوست ارسال میگردد.
7 | نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-01-03869 | 2022-04-13 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: