## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-PEDCO-320-PL-MT-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0058 |  |  | Transmital Date:8/22/2021
Document Title: MTO For Line Pipe |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PL-TR-0058 |  |  | Transmital Date:8/22/2021
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PL-MT-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه مدرك بر اساس مدارك مهندسي پايه تهيه گرديده است در این برهه نقطه نظر خاصی مطرح نیست. البته مدارك Pipeline Material Specification و Pipeline Wall Thickness Calculation بايستي ارائه گردد و تأييد نهايي مدرك منوط به ارائه مدارك فوق و نقشه Plan & Profile خط لوله مربوطه مي باشد. همچنين، بهتر است جهت خريد لوله حداقل 5 درصد Contingency در نظر گرفته شود. پیشبرد گام بعدی مهندسی بلامانع است. شایان ذکر است مسئولیت هر نوع نقص و یا کمبود در مدرک و مترا‍ژ لوله برآورد شده به عهده پیمانکار است. |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | با عنایت به ارسال و نهایی سازی تقریبی مدارک مرتبط و نیز توجه به دیر-تحویل بودن این آیتم، مدرک به روزرسانی و ارائه گردیده است.
2 | بهتر است در عنوان مدرك به 4" Condensate و 8" Gas اشاره گردد. |  | BK-SUR-ENG-PPL-00-01379 | 2021-08-22 | نقطه نظر مربوطه (با لحاظ نمودن نتایج مطالعات مهندسی ارزش) در ردیف MTO، به نحو مقتضی اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 22-Aug-2021 |  |  |  |  | Date : 22-Aug-2021