## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0035_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0694 |  |  | Transmital Date: 07/Mar/2022
Document Title: Mechanical Data Sheets For Glycol Drain Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-0694 |  |  | Transmital Date: 07/Mar/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0035_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please find the attched |  | BK-SUR-ENG-MEC-00-03398 | 2022-03-08 | Refer to attached pdf file for Hirgan reply
2 | اين مدرك براي ذينفع اصلي پروژه ارسال نشده است ، كامنت هاي داده شده اعمال گردد و مدرك جديد مجدا با همين شماره ويرايش جاگزين و ارسال شود. |  | BK-SUR-ENG-MEC-00-03398 | 2022-03-08 | این مدرک از طرف کارفرمای اصلی (مناطق نفت خیز جنوب) مورد بررسی و تایید قرار گرفته لذا نقطه نظرات مورد نظر اعمال و مدرک مربوطه با یک رویژن بالاتر ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 3/8/2022 |  |  |  |  | Date: 09/06/2022