## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0022_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1375 |  |  | Transmital Date: 09/Sep/2022
Document Title:Mechanical Data Sheets For Closed Drain Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0101-TR-1375 |  |  | Transmital Date: 09/Sep/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0022_D04 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | please specify the max values for Density and viscosity. |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | Noted
2 | NSS limitation shall be considered 213 |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | Not accepted, this requirement has not been mentioned in project specification and related standards. This requirement will be checked and finalized at vendor's offer stage.
3 | Insulation/ temp rise to be mentioned: F/B coupling to be balanced at least G2.5 |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | 1. Noted 2. Not accepted, this requirement has not been mentioned in project specification. As per clause 7.2.3 of API 610 and table1 of ISO 1940-1 standard, Grade G6.3 is sufficient.
4 | Test shall be in compliance with 8.3.3.2 & 8.3.3.3 |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | Noted
5 | Hydrostatic for bowl (WIT) barrel and pump shall have the same MAWP and to be hydrotest in same value with pump |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | 1. Noted 2. Noted, Will be added as note
6 | CONNECTION BOLTING (7.5.1.7) - shall be SS BEARING LIFE CALCULATIONS REQUIRED (6.10.1.6) to be mentioned YES OPERATION TO TRIP SPEED to be mentioned YES |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | 1. Noted, Connecting bolting will be specified SS 2. Noted, Bearing life calculation required will be mentioned YES 3. Not applicable for this pump. because the pump is constant speed
7 | MAXIMUM DISCHARGE PRESSURE TO INCLUDE "YES" it has mentioned yes but the max density has not specified |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | Noted, maximum density will be specified in next revision
8 | PRESSURE GAUGE TYPE MANIFOLD PIPING FOR PURCHASER CONNECTION (7.5.1.6): VENT /DRIAN SEPARTATE MOUNTING PLATE (9.3.8.3.1) PROVIDE SEPARATE SOLEPLATE (9.3.8.3.3) Above items to be mentioned YES |  | BK-SUR-ENG-MEC-01-05690 | 2020-09-13 | Noted (Please refer to attached pdf file for Hirgan reply)
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 9/16/2022 |  |  |  |  | Date: 11/23/2022