## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0024_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-800 |  |  | Transmital Date: 11/Apr/2022
Document Title: Mechanical Data Sheets For Flare KO Drum Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0101-TR-800 |  |  | Transmital Date: 11/Apr/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | متريال پمپ مي بايست از آخرين ويرايش مدرك Piping Corrosion Study & Material Selection Report "BK-GSC-PEDCO-120- .تبعيت داشته باشدPIRT-0001" |  | BK-SUR-ENG-MEC-01-03932 | 2022-04-16 | با توجه به نوع سیال و میزان خوردگی آن، متریال S-6 برای پمپ Flare K.O Drum کفایت می کند. لازم به ذکر است که متریال پمپ مذکور در ویرایش D01 مدرک Material Selection Report & Piping Corrosion Study; BK-GCS-PEDCO-120-PI-RT-0001 اصلاح گردید و از A-8 به S-6 تغییر پیدا کرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 4/16/2022 |  |  |  |  | Date: 09/06/2022