## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0990 |  |  | Transmital Date: 5/22/2022
Document Title: Process Main Equipment List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0990 |  |  | Transmital Date: 5/22/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مغایرت داده های مندرج در این مدرک با مدارک محاسباتی و نقطه نظرات مربوط به نقشه های P&ID و PFD ضروریست تا اطلاعات مندرج بروزرسانی گردد. |  | 1401-2294-104506 | 1401/03/25 | اعمال می گردد.
2 | پاسخ ارایه شده در بند 7 پاسخنامه مورد قبول نمی باشد. |  | 1401-2294-104506 | 1401/03/25 | در ارتباط با حداقل دمای تجهیزات برقی لازم به ذکر است که این دما مطابق با اسناد پیمان و مدرک Basis Of Design برابر با 5 درجه سانتی گراد در نظر گرفته شده و مورد تایید قرار گرفته است. ضمن آنکه سخترین شرایط در طراحی این تجهیزات دمای حد اکثری بوده و حداقل دما در این خصوص مطرح نمی باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: