## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0990 |  |  | Transmital Date: 5/22/2022
Document Title: Process Main Equipment List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0990 |  |  | Transmital Date: 5/22/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0001_D01 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظرات ارائه شده در خصوص ابعاد ظروف، پس از اعمال در محاسبات مربوطه در اين مدرك نيز بروزرساني گردد. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | اعمال می گردد.
2 | تغييرات صورت گرفته براساس توافقات با ذينفع اصلي در خصوص ميعانات، در اين مدرك درنظر گرفته شود. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | اعمال می گردد.
3 | نوشتن عبارت جنس Impller و Casing براي پكيج ها، كولر ها و... نياز به تصحيح دارد. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | کامنت فوق نا مفهوم می باشد.لطفا نقطه نظر را به صورت شفاف مطرح نمایید.
4 | درخصوص پكيج ها مي بايست ستوني براي ارائه توضيحات اضافه گردد كه مواردي مانند طول فلر، نوع احتراق و يا نقطه تنظيم شبنم پكيج نم زدا و يا ميزان تزريق مواد شيميايي باشد. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | اطلاعات تکمیلی تجهیزات فوق در مدارک Duty Spec و Data sheets موجود بوده و این مدرک صرفا جهت ارایه لیست تجهیزات تهیه گشته است.
5 | مسئوليت كامل بودن تعداد تجهيزات مندرج در اين مدرك با ساير مدارك بر عهده پيمانكار مي باشد. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | مورد تایید است.
6 | موارد مندرج بصورت VTA مي بايست توسط پيمانكار تكميل گردد. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | بعد از دریافت اطلاعات از سازنده اطلاعات فوق تکمیل می گردد.
7 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04737 | 2022-06-18 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: