## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0456 |  |  | Transmital Date: 12/JAN/2022
Document Title: Mechanical Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0456 |  |  | Transmital Date: 12/JAN/2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0102_D01 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات فرآیندی بر اساس آخرین ویرایش مدراک در مدرک گنجانده شود. |  | 00/2294/386693 | 1400/11/09 | نقطه نظر کارفرمای محترم اعمال شد.
2 | فشار عملیاتی مطابق اسناد پیمان در نظر گرفته شود. |  | 00/2294/386693 | 1400/11/09 | فشار عملیاتی برابر با 5.3 بارگیج با توجه به شبیه سازی صورت گرفته در مهندسی تفضیلی در نظر گرفته شده، ضمن آنکه این مقدار مطابق با مدرک PFD ذکر گردیده است.
3 | دلایل تغییر ابعاد مخزن نسبت به اسناد پایه بیان گردد. خاطر نشان می شود ادعای تغییر کار در این خصوص پذیرفتنی نیست. |  | 00/2294/386693 | 1400/11/09 | سایزینگ مخزن با توجه به آخرین اطلاعات فرآیندی محاسبه شده و در مدرک ِDrum Sizing موجود میباشد.
4 | الزام سازنده به ارایه کتابچه محاسبات و مدارک طراحی به عنوان یادداشت ذکر گردد. |  | 00/2294/386693 | 1400/11/09 | نقطه نظر کارفرمای محترم اعمال شد.
5 | تعیین میزان C.A. پس از انجام مطالعات خوردگی امکانپذیز خواهد بود. |  | 00/2294/386693 | 1400/11/09 | مطالعات خوردگی انجام شده و ارسال گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 9/7/2022