## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0002-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1217 |  |  | Transmital Date: 30/July/2022
Document Title: Mechanical Data Sheets For 1st Stage G.C. Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-1217 |  |  | Transmital Date: 30/July/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0002-D02 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نهایی نشدن مدرک Drum Sizing، دلایل تغییر ابعاد مخزن نسبت به استاد پیمان پذیرفتنی نیست. |  | 01/2294/183219 | 1401/05/26 | نظر کارفرمای محترم مد نظر قرار گرفت.
2 | فشار عملیاتی و طراحی مطابق با استاد پایه و آخرین اطلاعات فرآیندی اصلاح گردد. |  | 01/2294/183219 | 1401/05/26 | نظر کارفرمای محترم مد نظر قرار گرفت.
3 | لزوم انجام عملیات حرارتی در مدرک قید گردد. |  | 01/2294/183219 | 1401/05/26 | در صفحه 5 مدرک، قسمت Fabrication and Inspection Requirements اشاره شده است.
4 | اظهار نظر در خصوص میزان CA پس از نهایی شدن این مدرک امکان پذیر خواهد بود. |  | 01/2294/183219 | 1401/05/26 | نظر کارفرمای محترم مد نظر قرار گرفت.
5 | شماره یادداشت هایی که در ویرایش های پیشین از مدرک حذف شده است نشان داده نشود. |  | 01/2294/183219 | 1401/05/26 | نظر کارفرمای محترم مد نظر قرار گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 8/13/2022 |  |  |  |  | Date: 9/7/2022