## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0004-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0902 |  |  | Transmital Date:07/MAY/2022
Document Title: Mechanical Data Sheets For 2nd Stage G.C. Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-902 |  |  | Transmital Date:07/MAY/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0004-D02 |  |  | CRS Status: | CM
item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دلایل تغییر ابعاد نسبت به اسناد پیمان مشخص گردد. |  | 01/2290/89281 | 1401/03/16 | ابعاد مخزن بر اساس محاسبات انجام گرفته و گزارش مدرک DRUM SIZING مشخص شده است.
2 | آخرین ویرایش استاندارد IPS در بخش کد طراحی درج گردد. |  | 01/2290/89281 | 1401/03/16 | نظر کارفرمای محترم اعمال گردید.
3 | جنس صفحات متصل شده به مخرن با جنس بدنه مخزن باید یکسان باشد. |  | 01/2290/89281 | 1401/03/16 | در نوت 40 اشاره شده است.
4 | با توجه به نهایی نشدن مدرک Process Data Sheets for 2nd Stage G.C Suction Drums، ضرروی است آخرین تغییرات مدرک مذکور در این مدرک نیز اعمال گردد. |  | 01/2290/89281 | 1401/03/16 | نظر کارفرمای محترم اعمال گردید.
5 | این مخزن می بایست برای خلا داخلی طراحی گردد، لذا بند 14 مدرک تکمیل شود. |  | 01/2290/89281 | 1401/03/16 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 5/9/2022 |  |  |  |  | Date: 09/07/2022