## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0008_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0311 |  |  | Transmital Date: 07/DeC/2021
Document Title: Mechanical Data Sheets For Instrument Air Receiver |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0006-ME-TR-0311 |  |  | Transmital Date: 07/DeC/2021
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0008_D00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دمای عملیاتی مطابق با آخرین اطلاعات فرآیندی و اسناد پایه اصلاح گردد. |  | 01/2294/183214 | 1401/05/26 | نظر کارفرمای محترم اعمال گردید.
2 | ابعاد مطابق با اسناد پابه در نظر گرفته شود. |  | 01/2294/183214 | 1401/05/26 | ابعاد مخزن بر اساس محاسبات انجام گرفته و گزارش مدرک DRUM SIZING مشخص شده است.
3 | محاسبات مربوط به ضخامت مخرن و نازل ها به همراه مدرک ارسال گردد. |  | 01/2294/183214 | 1401/05/26 | مطابق نظرات کارفرما بر روی سایر مدارک، جرئیات ضخامت توسط سازنده نهایی می شود. در این مرحله این اطلاعات از مدرک حذف می شود.
4 | رنگ آمیزی مخزن مطابق با Spec مربوطه صورت پذیرد. |  | 01/2294/183214 | 1401/05/26 | نظر کارفرمای محترم اعمال گردید.
5 | مبنای درج پیش آمدگی نازلهای مخزن مشخص گردد. |  | 01/2294/183214 | 1401/05/26 | بر اساس استانداردهای پروژه شامل Standard drawing for pressure vessel و پروژه های پیشین.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 1/26/2022 |  |  |  |  | Date: 9/7/2022