## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0009-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0381 |  |  | Transmital Date: 26/Dec/2021
Document Title:MECHANICAL DATA SHEETS FOR NITROGEN RECEIVER |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0381 |  |  | Transmital Date: 26/Dec/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0009-D01 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه ابعاد مخزن در این ویرایش نسبت به ویرایش پیشین تغییر نموده است، ضروری است دلایل تغییر مشخصات ذکر گردد. در ضمن هر گونه تغییر نسبت به ویرایش قبل می بایست با علامت در مدرک مشخص گردد در حالی که تغییرات مذکور مشخص نشده است. |  | 00/29/342154 | 1400/10/09 | ابعاد مخزن بر اساس محاسبات انجام گرفته و گزارش مدرک DRUM SIZING مشخص شده است. نظر کارفرمای محترم مد نظر قرار خواهد گرفت.
2 | فشار طراحی مطابق با آخرین ویرایش مدرک فرآیندی در نظر گرفته شود. |  | 00/29/342154 | 1400/10/09 | با توجه به آخرین اطلاعات و طبق مدرک Process Data Sheet اصلاح گشته است
3 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان درج گردد. |  | 00/29/342154 | 1400/10/09 | اعمال شد.
4 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ضروری است معیار تعیین حداقل ضخامت ها در مدرک مشخص گردد. در ضمن چنانچه در این زمینه محاسبات اولیه صورت گرفته است ارائه آن ضرورت دارد. |  | 00/29/342154 | 1400/10/09 | با توجه به نظر کارفرما ضخامت ها از مدرک حذف شدند.
5 | الزام سازنده به ارائه کتابچه محاسبات و مدارک طراحی به عنوان یادداشت ذکر گردد. |  | 00/29/342154 | 1400/10/09 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 3/5/2022 |  |  |  |  | 2022-09-07