## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0010_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0339 |  |  | Transmital Date: 13/Dec/2021
Document Title:Mechanical Data Sheets For Close Drain Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0339 |  |  | Transmital Date: 13/Dec/2021
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0010_D00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | باتوجه به اینکه محاسبات طراحی ارسال نشده است، ملاک تعیین مشخصات طراحی (به عنوان نمونه ضخامت) چه بوده است. پیشنهاد می گردد تعیین اینگونه اطلاعات با هماهنگی سازنده صورت پذیرد. |  | 00/2294/331625 | 1400/10/01 | مقادیر ضخامت شل و هد از دیتاشیت حذف شد.
2 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان درنظر گرفته شود. |  | 00/2294/331625 | 1400/10/01 | نوت مذکور طبق نظر کارفرمای محترم اصلاح و به مدرک دستورالعمل تامین قطعات یدکی پیوست 11 کتابچه پیمان ارجاع داده شد.
3 | باتوجه به اینکه مطالعات خوردگی انجام نشده است، معیار انتخاب C.A مشخص گردد. |  | 00/2294/331625 | 1400/10/01 | مطالعات خوردگی انجام شده و ارسال گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: S.Salehi | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 9/7/2022