## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0013_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0342 |  |  | Transmital Date: 13/DeC/2021
Document Title:Mechanical Data Sheets For Fuel Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0342 |  |  | Transmital Date: 13/DeC/2021
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0013_D00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار و دمای طراحی / عملیاتی مطابق با اسناد پایه و اطلاعات فرآیندی پروژه در نظر گرفته شود. |  | 00/2294/336157 | 1400/10/05 | نظر کارفرمای محترم اعمال گردید.
2 | همان گونه که در اسناد پایه بیان شده است تعیین ابعاد و جهت تجهیز مذکور در مرحله مهندسی تفصیلی و با نظر سازنده تعیین خواهد شد لذا ضروری است ملاک تعیین مشخصات فوق در مدرک مشخص گردد. |  | 00/2294/336157 | 1400/10/05 | ابعاد و جهت تجهیز به صورت اولیه داده شده است و در صورت تغییرات احتمالی در آینده نهایی خواهد شد.
3 | با توجه به بند فوق و از آنجا که محاسبات و مستندات طراحی مخزن تا کنون ارسال نشده است و مطالعات خوردگی نیز ارائه نشده است، معیار طراحی و تعیین مشخصات نازلها مشخص گردد. |  | 00/2294/336157 | 1400/10/05 | مطالعات خوردگی انجام شده و ارسال گردیده است.
4 | در خصوص متریال پوشش مخزن میبایست مشخصات کامل مطابق با spec پروژه درج گردد و یا به دیگر مدارک مربوطه ارجاع شود. |  | 00/2294/336157 | 1400/10/05 | نظر کارفرمای محترم اعمال گردید.
5 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ملاک نعیین مشخصات طراحی (به عنوان نمونه ضخامت) چه بوده است. پیشنهاد میگردد تعیین اینگونه اطلاعات با هماهنگی سازنده صورت پذیرد. |  | 00/2294/336157 | 1400/10/05 | جزئیات ضخامت از مدارک حذف شده و با نظر سازنده اعمال خواهد شد.
6 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان درنظر گرفته شود. |  | 00/2294/336157 | 1400/10/05 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 09/10/2022