## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0036_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0436 |  |  | Transmital Date: 05/JAN/2022
Document Title: Mechanical Data Sheets For GLYCOL SUMP DRUM |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0436 |  |  | Transmital Date: 05/JAN/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0036_D00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم درج مدرک در لیست مدارک مهندسی پروژه، و از آنجا که مطابق اسناد پایه تجهیز مذکور در پکیج گلایکول در نظر گرفته شده است لذا ضروری است لزوم تولید مدرک بیان گردد. |  | 00/2294/372927 | 1400/10/30 | مطابق MDL تغییرات اعمال شده است.
2 | استاندارد طراحی مخزن مشخص نشده است. |  | 00/2294/372927 | 1400/10/30 | در بخش REFERENCE STANDARDS & DOCUMENTS اشاره شده است.
3 | اطلاعات فرآیندی نهایی شده ملاک عمل قرار گیرد. |  | 00/2294/372927 | 1400/10/30 | نظرات کارفرمای محترم اعمال گردید.
4 | مبنای طراحی پوشش داخلی مخزن بیان گردد. |  | 00/2294/372927 | 1400/10/30 | بر مبتای طراحی پایه در نظر گرفته شده است.
5 | مبانی طراحی ابعاد مخزن با در نظر گرفتن اطلاعات فرآیندی مشخص گردد. |  | 00/2294/372927 | 1400/10/30 | ابعاد مخزن بر اساس محاسبات انجام گرفته و گزارش مدرک DRUM SIZING مشخص شده است.
6 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ضروری است معیار تعیین سایز نازلها مشخص گردد. در ضمن چنانچه در این زمینه محاسبات اولیه صورت گرفته است ارایه آن ضرورت دارد. |  | 00/2294/372927 | 1400/10/30 | بر اساس اطلاعات مدارک فرآیند اعمال شده است.
7 | الزام سازنده به ارایه کتابچه محاسبات و مدارک طراحی به عنوان یادداشت ذکر گردد. |  | 00/2294/372927 | 1400/10/30 | در Note 1 مشخص شده است.
8 | میزان کالای یدکی مطابق با پیوست 11 کتابچه پیمان درج گردد. |  | 00/2294/372927 | 1400/10/30 | نظرات کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 01/03/2021 |  |  |  |  | Date: 09/07/2022