## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0456 |  |  | Transmital Date: 12/Jan/2022
Document Title: Mechanical Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0106-ME-TR-0456 |  |  | Transmital Date: 12/Jan/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-ME-DT-0102_D01 |  |  | CRS Status: | C3
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | میزان خوردگی مجاز بر اساس مطالعات خوردگی میبایست در نظر گرفته شده و ميزان آن در مدرك قيد گردد. |  | BK-SUR-ENG-MEC-00-03587 | 2022-03-15 | میزان خوردگی بر اساس مطالعات خوردگی در مدرک درج شده است.
2 | نت 12 مبني بر تعيين ميزان خوردگي توسط سازنده صحيح نبوده و ميزان خوردگي بر اساس مطالعات خوردگي تعيين ميشود. |  | BK-SUR-ENG-MEC-00-03587 | 2022-03-15 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 3/15/2022 |  |  |  |  | Date: 9/7/2022