## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0004-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0902 |  |  | Transmital Date:07/MAY/2022
Document Title: Mechanical Data Sheets For 2nd Stage G.C. Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-ME-TR-902 |  |  | Transmital Date:07/MAY/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0004-D02 |  |  | CRS Status: | C3
item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | HHLL : 1100 |  | BK-SUR-ENG-MEC-01-04179 | 2022-05-09 | اعمال شد
2 | ضخامت shell , head مشخص گردد. / ضخامت ورق مشخص گردد. |  | BK-SUR-ENG-MEC-01-04179 | 2022-05-09 | مطابق نظر کارفرمای اصلی (NISOC) ضخامت ها در این مقطع در مدارک مشخص نمیشود.
3 | SA516Gr.70N / SA283 Gr.C / SA106 Gr.B / SA105N / SA234 Gr.WPB |  | BK-SUR-ENG-MEC-01-04179 | 2022-05-09 | مطابق استاندارد ASTM به صورت A 516 و... درست است.
4 | جانمایی نازل ها در orientation view با نمای سمت چپ تناقض دارد. |  | BK-SUR-ENG-MEC-01-04179 | 2022-05-09 | نمای سمت چپ نمای elevation است و تنها ارتفاع نازلها در آن مد نظر است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 5/9/2022 |  |  |  |  | Date: 9/7/2022