## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0009-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0381 |  |  | Transmital Date: 26/Dec/2021
Document Title:MECHANICAL DATA SHEETS FOR NITROGEN RECEIVER |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0381 |  |  | Transmital Date: 26/Dec/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-320-ME-DT-0009-D01 |  |  | CRS Status: | C3
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | please find the atatched commets |  | BK-SUR-ENG-MEC-00-03340 | 2022-03-05 | Process data in this document is based on PDS. If under any circumstances, condense is carried to the vessel, only one level named " Liquid Level " is considered and drain will be opened when liquid reaches that level (300 mm).
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 3/5/2022 |  |  |  |  | Date: 9/7/2022