## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0036-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0436 |  |  | Transmital Date: 05/Jan/2022
Document Title: MECHANICAL DATA SHEETS FOR GLYCOL SUMP DRUM |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0436 |  |  | Transmital Date: 05/Jan/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0036-D00 |  |  | CRS Status: | C3
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Please find the atatched comments. |  | BK-SUR-ENG-MEC-00-02941 | 2022-02-05 | All comments were implemented, otherwise clarified as below.
2 | Data Sheet is not compatible with P&ID |  | BK-SUR-ENG-MEC-00-02941 | 2022-02-05 | Data are revised based on the latest Process data.
3 | min THK shall be specified |  | BK-SUR-ENG-MEC-00-02941 | 2022-02-05 | Based on NISOC comments, at this stage thickness is not required. It should be specified by vendor.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature H.naserizadeh |  |  |  | Clarified By: H.Adineh | Signature
| Date: 31/01/2022 |  |  |  |  | Date: 09/07/2022