## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0013_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0342 |  |  | Transmital Date: 13/DeC/2021
Document Title:Mechanical Data Sheets For Fuel Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0342 |  |  | Transmital Date: 13/DeC/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0013_D00 |  |  | CRS Status: | C3
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | please find the atatched commets |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | All of the comments were implemented otherwise clarified as below.
2 | PWHT due to process |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | It was already mentioned
3 | Drain (D),Utility Connection (S),Pressure Gauge (P1), Level Switch HH ( L5,6) ID= 438 |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | Please recheck with regard to the latest Process documents.
4 | SA 106 Gr B (18" Pipe, Sch. STD) |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | Vessel diameter was too small (~400mm), so it is not possible to roll sheet metal and pipe was chosen as shell material.
5 | Operating Temperature, Liquid Sp. Gravity, MDMT |  | BK-SUR-ENG-MEC-00-02543 | 2022-01-03 | Revised with regard to the process changes.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M.Fakharian
| Date: 01/03/2022 |  |  |  |  | Date: 09/10/2022