## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0009_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0588 |  |  | Transmital Date: 13/Feb/2022
Document Title: PMR For Centrifugal Pumps For Process Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-ME-TR-0588 |  |  | Transmital Date: 13/Feb/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0009_D00 |  |  | CRS Status: | C3
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Scope of supply shall be exactly specified based on battery limits. So please find the attached file. |  | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | Please mention your comment about scope of supply clearly. Refer to attached file for reply.
2 | Attachment 2 shall be revised based on proosed pump |  | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | Please mention your comment clearly and exactly.
3 | Latest edition of documents which are approved shall be mentioned in attachments. |  | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | Noted, Latest edition of issued documents are mentioned in attachments. In addition, latest edition of documents was updated.
4 | Priority of document shall be mentioned a) Purchase order/Technical Clarification(TCL) b) Agreed Exception/Deviation c) Material Requisition d) Data Sheet/Drawing e) Project Specification f) International codes & standards |  | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | According to the project format, any conflict between this document and other project document or reference standards, this issue must be reported to the client and The final decision in this situation will be made by CLIENT. This issue is mentioned in paragraph 3 of the document.
5 | Please add below note:Commissioning and start‐up spare parts shall be listed in a separate form. During bid stage, Vendor shall submit a detailed list of spare parts together with backup documentation and drawings, specifying quantities. Two years spare parts shall be listed in a separate from and quoted as separate optional price and the price shall be valid for 6 months after purchase order. |  | BK-SUR-ENG-MEC-00-03354 | 2022-03-05 | Noted, For Hirgan reply refer to attached pdf file.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 3/5/2022 |  |  |  |  | Date: 9/7/2022