## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0004_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0857 |  |  | Transmital Date: 24 Apr 2022
Document Title: ESD Level Hierarchy - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0012-IN-TR-0857 |  |  | Transmital Date: 24 Apr 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0004_D00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اين مدرك با مدرك ESD Philossophy تناقض دارد... ESD-0 و ESD-1 براي Manifold در مدرك مربوطه تعريف نشده است. |  | BK-SUR-ENG-INS-01-04192 | 2022-05-08 | مجدد بررسی شد. محتوای درج شده درنسخه اولیه مدارک کاملا منطبق است. این نسخه از مدرک با توجه به آخرین تغییرات به روز رسانی شده است.
2 | Push Button ها در اين مدرك تعريف نشده است. |  | BK-SUR-ENG-INS-01-04192 | 2022-05-08 | در این بسته کنسول و دکمه ESD تعریف نشده است.توضیحات به صورت نوت اعمال گردید.
3 | مدرك P&ID منطبق با مدرك ESD Heirarichy نيست... لطفا مدارك اصلاح گردد. |  | BK-SUR-ENG-INS-01-04192 | 2022-05-08 | مجدد بررسی شد. محتوای درج شده درنسخه اولیه مدارک کاملا منطبق است. این نسخه از مدرک با توجه به آخرین تغییرات به روز رسانی شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 8 May 2022 |  |  |  |  | Date: