## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-PY-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0935 |  |  | Transmital Date: 11 May 2022
Document Title:Control Room Layout & Arrangement Drawing - Extension of Binak B/C Manifold |  |  |  |  | EPC Contractor Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-0935 |  |  | Transmital Date: 11 May 2022
[5 empty] | CRS No:NISOC- BK-W007S-PEDCO-110-IN-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ابعاد همه تابلو ها در مدرک درج شود. |  | 01/2294/104511 | 1401/03/25 | مطابق خواست کارفرمای محترم اعمال شد
2 | فضای تجهیزات مهندسی( DCS EWS و ESD EWS و چاپگرهای مربوطه و...) مجزا از تجهیزات اپراتوری در نظر گرفته شود. |  | 01/2294/104511 | 1401/03/25 | با توجه به محدودیت فضای اتاق ، امکان ایجاد فضای جداگانه با پارتیشن نمیباشد، مطابق خواست کارفرمای محترم میزجداگانه برای این ادوات تخصیص داده شد.
3 | نقشه تکمیل و اصلاح گردد. به عنوان نمونه ESD Console و یک دستگاه چاپگر سیاه وسفید نشان داده نشده است. |  | 01/2294/104511 | 1401/03/25 | مطابق خواست کارفرمای محترم اعمال شد ( لازم به ذکر است کنسول ESD برای کلاستر در نظر گرفته نشده و دکمه ESD روی در پانل موجود قرار دارد)
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 28 May 2022 |  |  |  |  | Date: