## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-SP-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1147 |  |  | Transmital Date: 13/JUL/2022
Document Title: Specification for Pressure Vessels |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-1147 |  |  | Transmital Date: 13/JUL/2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-ME-SP-0001_D01 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با در نظر گرفتن ارجاع این مدرک به استاندارد IPS-G-ME-150(2) شماره سرفصلهای اصلی به اشتباه درج شده است، لذا مدرک نیاز به بازنگری کلی دارد. |  | 01/2294/180896 | 1400/05/25 | مدرک با توجه به مدارک پایه و نظر کارفرمای محترم صورت کلی بازنگری شده و ارسال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 09/10/2022