## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0014-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0389 |  |  | Transmital Date: 28/Dec/2021
Document Title: Mechanical Data Sheets For Slug Catcher |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-0389 |  |  | Transmital Date: 28/Dec/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0014-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دلایل تغییر ابعاد مخزن نسبت به اسناد پایه بیان گردد. خاطر نشان میشود ادعای تغییر کار در این خصوص پذیرفتنی نیست. |  | 00/2294/352384 | 1400/10/16 | ابعاد مخزن بر اساس محاسبات انجام گرفته و گزارش مدرک DRUM SIZING مشخص شده است.
2 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ضروری است معیار تعیین حداقل ضخامتها در مدرک مشخص گردد. در ضمن چنانچه در این زمینه محاسبات اولیه صورت گرفته است ارائه آن ضرورت دارد. |  | 00/2294/352384 | 1400/10/16 | با توجه به نظر کارفرما ضخامت ها از مدرک حذف شدند.
3 | الزام سازنده به ارائه کتابچه محاسبات و مدارک طراحی به عنوان یادداشت ذکر گردد. |  | 00/2294/352384 | 1400/10/16 | اعمال شد.
4 | درج کالای یدکی در این مدرک و قرار دادن آن در تعهد سازنده مخزن، مقبولیت ندارد. می بایست اقلام یدکی در دیگر مدارک مرتبط لحاظ گردد. |  | 00/2294/352384 | 1400/10/16 | اعمال شد.
5 | تعیین میزان C.A پس از انجام مطالعات خوردگی امکان پذیر خواهد بود. |  | 00/2294/352384 | 1400/10/16 | مطالعات خوردگی ارسال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Adineh | Signature
| Date: 03/05/2022 |  |  |  |  | Date: 9/11/2022