## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ME-DC-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1104 |  |  | Transmital Date: 6/21/2022
Document Title: Mechanical Design Criteria |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-1104 |  |  | Transmital Date: 6/21/2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-ME-DC-0001_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه در دیگر بندها نیز نسبت به ویرایش قبلی تغییرات ایجاد شده است ضروری است دلایل بروز این تغییرات مشخص گردد. |  | 01/2294/170190 | 1401/05/18 | تغییرات با توجه به پروژه های مشابه و نقطه نظرات شرکت PEDCO اعمال شده است.
2 | موارد مطروحه در بند 8، Reply Sheet اصلاح نشده است. |  | 01/2294/170190 | 1401/05/18 | نظر کارفرمای محترم اعمال گردید.
3 | در پاسخ به بند 14، Reply Sheet به اطلاع می رساند موارد مندرج در بند 7.5 تغییر داده نشده است و تنها عنوان بند تغییر یافته است. |  | 01/2294/170190 | 1401/05/18 | نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.behbahani | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature
| Date: 6/29/2022 |  |  |  |  | Date: 9/12/2022